## Sheet1
Description | Assessment | Risk | Impact | Responsibility | Current Mitigation | Proposed Mitigation | Response
Database is attacked and breached | Information stored in the database is exposed to the attackers, attackers could used the said information to cause harm to the database through the website. The data stored inside is not sensitive outside the application | Low | High | Me | None, the attacker will be able to remove trainees from the database | Implement back-end code to increase resilience against these attacks. Implement a hashed password so that attackers won't be able to harm the database using the information from the database | Bring the database offline, change usernames and add the removed trainee back if possible.
Database is deleted by attackers | Trainers and trainees won't be able to login, causing a fall on reputation | low | High | Me | None | Back up database on a different machine | Rebuild the infracture, as it is built through SQLAlchemy, it will be built back easily. Infrom trainers to recreate their account and add their trainees
HTTP traffic is monitored by an attacker | Attacker could be monitoring information sent through network | High | High | Me | None | Set up Https connection, encrypting the information going between the system | It will be extremely difficult to find out, if known, simply change every usename in the database and inform the trainers and trainees
SQL database goes dark | If GCP shuts down, database will go dark | low | low | Google Cloud Platform | None | Set up a different database with a different provider | Bring the website down and contact GCP.
Web server goes dark | If GCP shuts down, VM running the web server will shut down | low | low | Google Cloud Platform | None | Set up a different vm with a different provider | Start a new VM, pull code down from git hub and continue the webpage. Contact GCP
Anyone can register as Trainer | Using the registering form, anyone can register as a trainer even an attacker and could fill the database with fake trainees | low | high | Me | None | Set up a secret code that is needed when registering | Delete the data added during the attack
Trainer_username could be leaked | Using the trainer's username, the trainer's trainees could be deleted | medium | low | Trainer | None | Implement password to make the login process more secure | Change Trainer's username and ask them to add back their trainees
Exact URL could be used to overcome logins | Using exact URL for webpages, attacker could bypass login | high | low | Me | None | implement login restricted webpages and redirect exact url back to index page